## Slide 1: Apache Tomcat for Python
Luka Benzia
Seminar BIS
SS 2021

## Slide 2: Inhaltsverzeichnis
1. Introduction
  1.1 Overview
  1.2 Structure
2. Background
  2.1 What is Apache Tomcat?
  2.2 What is Python?
3. Installation
  3.1 Python Installation
  3.2 Apache Tomcat Installation
4. Programming part
  4.1 Implement Python
  4.2 Testing and Debugging
5. Nutshell Examples
  5.1 Different Nutshell Examples explained
  5.2 Instructions how to use them
6. Summary

## Slide 3
2021
2021
Today
Mar
Apr
May
2021
51 days
Mar 10 - May 19
Seminararbeit Apache Tomcat for Python
6 days
Mar 10 - Mar 17
Erste Bearbeitung des Themas
3 days
Mar 14 - Mar 17
Erstellung der Präsentation + Gantt-Chart
11 days
Mar 18 - Apr 1
Vertiefende Recherche
22 days
Apr 1 - May 1
Programmierphase
10 days
Apr 22 - May 5
Nutshell Beispiele erstellen
11 days
May 5 - May 19
Dokumentation schreiben
3 days
May 15 - May 19
Endpräsentation vorbereiten
Gantt - Chart